## Slide 1: Moving Employee Email to the Cloud with Microsoft Office 365
Mid-Atlantic Regional Educause Conference
Wednesday, January 16, 2013
Rick Gould, Director of Special Projects
Joseph Rossmeier, Vice President for Technology Services
Prince George’s Community College

## Slide 2: About the College
Prince George’s Community College
Central Maryland, founded in 1965
42,000 students using Microsoft live@edu in the Cloud
3,000 Employees using Microsoft Office 365 in the Cloud
JR

## Slide 3: Employee Email
Decision: January 2012
Novell GroupWise 6.5 (9 years old) - obsolete
  Lacked full integration with MS Office
  Incompatible with Windows 7
  Frequent downtime due to infrastructure problems
  Email Administration maintenance skills – limited to one shift
  End-User skills – held in the past by old technology

## Slide 4: Alternatives
Improve the status quo
  Continue based upon legacy decisions
  Stay with Novell and GroupWise - upgrade to latest release
  Easy to accomplish - but little technological advancement
Do something Strategic/ Transformational
  Replace earlier decisions (abandon the past)
  Change to Microsoft and Outlook / Exchange – YES !
  Change from on-site to the Microsoft Cloud – MAYBE ?

## Slide 5
EMAIL
INFRASTRUCTURE
----------
REQUIRED POINTS OF INTEGRATION
Employee Email
Email access through
College Website and Portal
PC / MAC
Email Clients
Web Browsers
Classrooms
Labs / Library
Student Email live@edu converting to Office 365 in 2013
Mobile Device
Apple
Android
Windows
Integration with Windows
MS Office
SharePoint

## Slide 6: Technology Strategies Satisfied by Outlook / Exchange
World-Class Providers
Enterprise Class Products
*Market-Leading Products and Services
*Integration with Microsoft Core Roadmap
*Long-lived solutions
*Integrated with other College technology plans
Integration with other Office 365 services
  SharePoint Online
  Office Web Parts
  LYNC Conferencing
Outsource Commodity Technologies
*Minimal/No Customization
IT skills already in-house or readily available

## Slide 7: Benefits for the End-User Provided by Outlook / Exchange
Up-to-date Technology
*Integration with MS Office
*Mobile device support
*Outlook Web App for remote access
*Outlook 2011 for MACs
Enables Windows 7, 8
*Satisfy or exceed end-user requirements
Easy access to training and Outlook communities
Users approve this change
User skill requirements are reasonable and attainable through training and practice; no hiring req’d
*Users will experience no or minimal workload change

## Slide 8: What about the Cloud?
Student email already in the Cloud
42,000 students using live@edu in the Microsoft Cloud
College experience with Microsoft student email – positive !
Live@edu scheduled to become Office 365 for Students
What about the email for employees?
Will IT and Users be better off with or without the Cloud?

## Slide 9: Benefits for IT Provided by the Office 365 Cloud
*24/7/365 operations
*99.9% availability
World-Class datacenter(s)
Infrastructure redundancy
Storage as a service
Performance as a service
Backup and recovery
Patch management
Release management
*System Development
*No customization needed
Integrated with MS Office
*Integrated with all of O365
Integrated with Office 365 for students
Integrated with Microsoft core roadmap
*Cost is reasonable or better

## Slide 10: Benefits for End-Users Provided by the Office 365 Cloud
*More storage - 25GB
Legal Hold (available, fee)
Unlimited Archive (available, fee)
Faculty and Students both using Office 365
Future integration with SharePoint Online and Lync Online
End-User experience - equal or better

## Slide 11: Project Cost Analysis
Cost
Cost Recovery
Consulting:
  original - $75K
  add’l migration - $56K
Quest Assistance - $17K
Quest Migration Tool - $35K
Total - $183K
Novell licenses - $70K / yr
Infrastructure freed up
  Servers - $30K/yr
  Storage - $20K/yr
  Backup - $10K/yr
  Other – $10K/yr
  Network Admin - $ ???
Total - $140K
Cost Recovery in 1.25 yrs

## Slide 12: Project Schedule --9 months
Jan - Contracts with Bell TechLogix, Quest and Microsoft
Feb – May
  Active Directory Preparation, Provision O365, load email accounts to O365; virtualize the GW client ; rollout Outlook 2010; user training and practice with Outlook & OWA
June – migrate data from GW to O365; go live 06/30 !
July to Sep – additional time required to migrate data
Oct 1st week – final migrations of the latest GW data
Oct 2nd week – prepare for cut-over & end user support
Oct 3rd week – cut-over; weekend of Oct 20

## Slide 13: Project Components
Active Directory Tune-Up
Provision Office 365
Establish email accounts
Project Communications
  Announcements, Portal Page
Train Users
  In Classroom, Tutorials
User practice in advance
Final Migrations
Cut-Over to O365
Support Users
Migrate email
  6 months current
  3 years archived
Migrate calendars
Migrate contacts
Migrate document files
Migrate distribution lists
Migrate rooms, etc.
Migrate resource accounts
Migrate permissions

## Slide 14: Unexpected Migration Problems
Migration Tool from Quest (not fully ready for Office 365)
Data movement to the Office 365 Cloud was slow
  1.25 GB/hour at best; throttled by Microsoft
  20 migration servers, 2400 hours runtime for migrations
Migration Errors
  Calendar - recurring meetings did not migrate
  Permissions - did not migrate
  Unpredictable - partial migrations per user
  Error report unreadable; causing selective re-runs

## Slide 15: Surprises about Office 365
Sync from Active Directory to Office 365 – once every 4 hrs
Global Address List (GAL)
  Office 365 updates and distributes the GAL once every 24 hours
Deleting Accounts
  Office 365 enables deleted accounts to be recovered for 30 days
  When an account is to be deleted, must petition MS to force an actual delete

## Slide 16: More Surprises
Search and Destroy – took over 20 hours to run a script across the Office 365 cloud to find and purge an email
Desktops that are not all at the same release, patch and registry level – act differently
  Sent / deleted email saved in wrong account unless patched
  Save and Send – works under Win 7, not under XP
College infrastructure needs to be “ready”
  Not quite like web browsing; email more interactive
  Bandwidth, PCs, MACs, network, wireless, AD, email admin

## Slide 17: Still More Surprises
Large mailings can’t go out through Office 365
  Limit of 1500 emails per 24 hrs per sender
  Need an in-house email server to relay the large mailings
Existing Fax Server was not compatible with Office 365
  New Microsoft –endorsed fax server being purchased (RightFax)
Anti-Spam service in Office 365
  Experiencing more spam, especially phishing
  May have to upgrade to the “preferred” service (fee)

## Slide 18: And Even More Surprises
Large data moves (cut/copy/paste) can take hours
  Example: moving 1000 contacts to a different folder
  Cloud can take as long as overnight to complete
End-Users with Outlook at Home
  Home PC does not have same patches / registry as office PC
  Outlook may act differently at home

## Slide 19: The Best Surprise
Users very happy with new email system—minimal complaints!

## Slide 20: Mobile Device Support
Microsoft ActiveSync
  Developed online consent form for end-user sign-up
  Email, Calendar and Contacts
  Apple (154 current users), Android and Windows next
Communication to Mobile Device from the Office 365 Cloud
  Wi-Fi and cellular communication channels
  Working fine, on and off-campus

## Slide 21: Fee-based add-on services
Legal Hold
  Used to support HR and litigation activities
  Prevents actual deletion of email
  Undetectable by end-user
  $4.50 per month per email account
Unlimited Archive
  Used for departmental accounts with large histories
  Accounting, Procurement
  $4.50 per month per email account

## Slide 22: Now Live on Office 365
Live on Office 365 since Oct 20 (~ 3 months)
No outages or major system-wide disruptions
One (1) email delivery slow-down lasting 4 hours

## Slide 23: Microsoft vs Quest
Microsoft Outlook / Exchange technology – no problems
Microsoft Office 365 Cloud technology – no problems
Surprises associated with the Microsoft Office 365 Cloud
  Appeared to be problems at first
  OK after we made the appropriate adjustments!!!
Data Migration using Quest Technologies – problems

## Slide 24: If we could do it all again….
Reduce the migration task:
  Migrate less history – we brought over 3 years
  Migrate fewer accounts – purge before migrating
  “Zero-Impact Migration Service” from Dell & Quest
  They will remote in and perform the migration for you
  Cloud-based migration service - no installation tasks
Quest “Co-Existence” Tool
  enables cut-over in phases (by department, campus, etc)

## Slide 25
Employee Data from Ellucian Colleague
Active
Directory
Office 365
Using Ellucian Colleague as the “system of record” to manage Active Directory and Office 365 Accounts

## Slide 26: Using Ellucian Colleague
Employee data extracted from Colleague
  Used to update Active Directory every day
  AD automatically sync’s to Office 365
Using Colleague data for:
  New hires, separations, retirements
  To automatically populate the Dynamic Distribution Lists
  Annual purge of email accounts

## Slide 28: Security Improvements
No email accounts
  For Student Employees, Contractors, Volunteers and
  Credit/ ConEd Adjuncts “off-the-payroll” 18 months or more
Deletion of email after 3 years
  Automatic deletion on a rolling 3 year schedule
Restrictions on Distribution Lists
  DLs have a moderator and use is limited to selected employees
Auto-Forwarding to other Email Systems – blocked

## Slide 29: Office 365 Academic Plan A2 More features in current release
We implemented:
  Exchange plan 1
Subscribed to 5 licenses of Exchange Plan 2 to get
  Legal Hold
  Can assign the 5 licenses to any 5 email accounts
Also available in Plan A2
  SharePoint Plan 1
  Lync Plan 1
  Office Web Apps

## Slide 31: Next Release of Office 365
New Features
New Features
Office on Demand - stream Office to end-points
Site Mailboxes – docs and email sync’d to SharePoint
Data Loss Prevention
eDiscovery Center
Context tracking - what people are working on
Work across Time Zones
Data governance / protection policies in SharePoint
Lync Meeting – HD video, VOIP, IM, desktop & doc sharing using the browser-based Lync web app
More details here…
www.microsoft.com/office/preview/en/office-365-enterprise

## Slide 32: Our Conclusion
Good Decisions
  Replace GroupWise with Outlook / Exchange
  Office 365 in the Cloud
Users like it, IT likes it
IT looking for additional Cloud opportunities

## Slide 33: Your Questions, Observations, etc.
Thank you
jrossmeier@pgcc.edu
rgould@pgcc.edu