## 0053
Project Name |  |  |  | Date: | 2013-02-25
| ACCC-0053 Cellular Distributed Antenna System |  |  | Score: | 66.5
|  |  |  | Max: | 200
Summary
| Required Effort |  | Rating | Maximum Rating | % of Max Rating
| Requested Designation as "needs to get done" |  | 0 | 100 | 0%
| Required Effort Value Total: |  | 0
Required effort adds 100 points to project value. This will set a value from 100 to 200.
| Project Value |  | Rating | Maximum Rating | % of Max Rating
| Number of Affected Customers |  | 31.5 | 35 | 90%
| Service Improvement |  | 35 | 35 | 100%
| Interdependencies |  | 18 | 30 | 60%
| Project Value Total: |  | 66.5
| Probability of Success |  | Rating | Maximum Rating | % of Max Rating
| Senior Management Commitment |  | 24 | 24 | 100%
| Stakeholder Commitment |  | 24 | 24 | 100%
| Project Management |  | 14 | 28 | 50%
| Institutional Readiness |  | 16 | 24 | 66.67%
| Probability of Success Total: |  | 78
| Risk Assessment |  | Rating | Maximum Rating | % of Max Rating
| Implementation timeline |  | 10 | 50 | 20%
| Urgency |  | 10 | 50 | 20%
| Total Risk: |  | 20
Chart
|  |  | Risk Assessment | 20
|  |  | Probability of Success | 78
|  |  | Project Value | 66.5
|  |  | Required Effort | 0
Required Effort (+100 to Project Value) |  |  | Score | Weight | Weighted Score
| Requested Designation as "needs to get done" |  | 0 | 100% | 0
| Yes due to Audit, Legal, End of Life, or Chancellor request. | 100
| No | 0
Project Value (1-100) |  |  | Score | Weight | Weighted Score
| Number of Affected Customers |  | 9 | 35% | 31.5
| Benefits all departments on campus, plus departments on other campuses. | 10
| Benefits most departments on campus. | 9
8
7
| Benefits over half of the departments and colleges on campus. | 6
5
4
| Benefits more than three, but not all, departments on campus. | 3
| Benefits two to three departments on campus. | 2
| Benefits ACCC only (internal project). | 1
|  |  | Score | Weight | Weighted Score
| Service Improvement |  | 4 | 35% | 35
| Will greatly improve operating efficiency and/or greatly improve customer perception of service. | 4
| Will moderately improve operating efficiency and/or moderately improve customer perception of service. | 3
| Will nominally improve operating efficiency and/or nominally improve customer perception of service. | 2
| Will not improve operating efficiency and/or nominally improve customer perception of service. | 1
|  |  | Score | Weight | Weighted Score
| Interdependencies |  | 3 | 30% | 18
| Positively impacts more than two projects. | 5
| Positively impacts one or two projects. | 4
| Does not impact other projects. | 3
| Negatively impacts one or two projects. | 2
| Negatively impacts more than two projects. | 1
Probability of Success (1-100) |  |  | Selection | Weight | Weighted Score
| Senior Management Commitment |  | 5 | 24% | 24
| There is broad management support for this project. | 5
4
| There is moderate management support for this project. | 3
2
| There is nominal management support for this project. | 1
|  |  | Selection | Weight | Weighted Score
| Stakeholder Commitment |  | 5 | 24% | 24
| There is broad stakeholder support for this project. | 5
4
| There is moderate stakeholder support for this project. | 3
2
| There is nominal stakeholder support for this project. | 1
|  |  | Selection | Weight | Weighted Score
| Project Management |  | 1 | 28% | 14
| Uses project management life cycle (PMLC). | 2
| Does not use a project management life cycle (PMLC). | 1
|  |  | Selection | Weight | Weighted Score
| Institutional Readiness |  | 2 | 24% | 16
| The sponsoring organization is ready to provide required project resources upon approval and there are no other barriers to project initiation. (1) | 3
| The sponsoring organization will need to secure/prioritize required project resources upon approval or there may be other barriers that inhibit proceeding with project. (.80) | 2
| The sponsoring organization is unable to commit the required project resources upon approval or other barriers inhibit proceeding with project. (0) | 1
Project Risk (1-100) |  |  | Selection | Weight | Weighted Score
| Implementation Timeline |  | 5 | 50% | 10
| The proposed timeframe for implementation is unlikely to be met. | 1 | 100
|  | 2 | 80
| There is a moderate risk that the proposed timeframe for implementation may not be met. | 3 | 60
|  | 4 | 40
| The proposed timeframe for implementation is reasonable and attainable. | 5 | 20
|  |  | Selection | Weight | Weighted Score
| Urgency (Risk Factor) |  | 5 | 50% | 10
| Loses all value if not completed by a specific date. | 1 | 100
|  | 2 | 80
| Loses most value if not completed by a specific date. | 3 | 60
|  | 4 | 40
| Keeps majority of value if not completed by a specific date. (start of semester, before law goes into effect) | 5 | 20